[image: image1.png]g
Ulster
lUn|vasiw



                         DRAFT REF 2029 Operational Timetable                                            [image: image2.png]



(This timetable represents the current project plan; it will be updated as the exercise progresses).
	NATIONAL TIMELINE
	ULSTER’S TIMELINE
	R&I Lead/Team
	

	2025 Spring
	

	
	· Develop first draft of the Code of practice 
· REF2029 CoP Working Group initial meeting 
· University wide consultation on the processes within Code of Practice 
	  Head of Research Performance (ND)
	

	· PCE Pilot project: 
· submission deadline (19 March 25)
· pilot panels assessing submissions

	· Preparation of Institutional PCE Statement (FC)
· Preparation of UoA Level PCE Statements (RDs)
· Completion of Feedback forms (RP Staff and RDs) (30 May 2025)
	 Research Performance team with Relevant RDs.
	

	· Application closes for joining the REF panels (28 April)
	· ADRIs/RDs to encourage applications
	  ADRIs/RDs
	

	2025 Summer
	

	
	· REF Reviews to discuss the progress of the submission for each UoA (May/June)
	PVCR/Research Performance/RDs
	

	· Publication of Guidance on Contribution to Knowledge and Understanding Policy and associated Codes of Practice 
	· Code of Practice - internal consultation with RDs
	Research Performance & RDs
	

	· Full panel membership announced
	
	
	

	2025 Autumn
	

	· REF paused
	
	
	

	· HESA Staff Data 2024-25 to be used as part of pilot to calculate Volume Measure
	· HESA Data on Staff for period 1st August 2024 – 31st July 2025 to be used to calculate UU’s Volume Measure as 
     part of pilot
	Research Performance (BW and SH) will work with RDs & P&C to confirm SRR Status and ensure PeopleXD is up-to-date for the HESA 24/25 Return

	 

	
	· Code of Practice – University wide consultation
	Research Performance
	

	
	· 1st Equality Impact Assessment of SRR/Non-SRR Staff 
   
	Head of Research Performance & EDI Team
	

	2025 Winter
	

	· PCE pilot project: sub-profile feedback provided to HEIs
	
	
	

	· Weightings confirmed for REF 2029
	
	
	

	· Engagement and Impact guidance published
	
	
	

	· Strategy, People and Research Environment guidance published
	
	
	

	· People, Culture and Environment (PCE) Pilot Report published 
· People, Culture and Environment (PCE) Indicators Report published, including community engagement and feedback 
	
	
	

	· Expert panels meet to begin development of guidance and        criteria
	
	
	

	
	· Launch of internal REF website
	Research Performance (BW) with MarComms Team
	

	
	· REF Reviews to discuss the progress of the submission for each UoA (Jan 26)
	 Research Performance/PVCR/RDs
	

	
	· 2nd Equality Impact Assessment of SRR/Non-SRR Staff 
	 Head of Research Performance (ND)/EDI

	

	2026 Spring
	

	
	· Strategy, People, and Research Environment Workshop for RDs (16 April 26)
	Chair of the Research Culture Steering Committee &
Institutional Lead for SPRE (SMcI)/RDs
	

	
	· Submit Code of Practice (15 May 2026)
	Head of Research Performance (ND)
	

	2026 Summer
	

	
	· First meeting of the REF Steering Group (15 June)
	Research Performance/PVCR
	

	
	· First meeting of the SPRE Working Group (30 June)
	Institutional Lead for SPRE (SMcI)/Research Performance 
	

	
	· Deadline for SRR decisions to be made for inclusion of staff in the 25/26 HESA return (30 June)
	Research Performance (BW)/RDs
	

	2026 Autumn
	

	· Final Guidance on Submissions and Panel Criteria and Working Methods published
	
	
	

	
	· REF Reviews (ICS focussed workshop for each Faculty)
	Institutional Lead for Innovation and Research Impact (TB)/Engagement & Impact/RDs
	

	2026 Winter
	

	· Special requests process launched
	
	
	

	· Publication of anonymised REF 2029 Steering Group and Panel meetings minutes and papers covering January 2023 to September 2026 (planned for December 2026) 
	
	
	

	
	· 3rd Equality Impact Assessment of SRR/Non-SRR Staff 
	 Head of Research Performance (ND)/EDI

	

	2027 Spring
	

	· Survey of submission intentions opens
	
	
	

	
	· REF Reviews to discuss the progress of the submission for each UoA 
	PVCR/Research Performance/RDs
	

	2027 Summer
	

	
	· Deadline for SRR decisions to be made for inclusion of staff in the 26/27 HESA return (30 June)
	 Research Performance (BW)/RDs
	

	· Survey of submission intentions closes
	
	
	

	· Special requests closes
	
	
	

	2027 Autumn
	

	
	· REF Reviews to discuss the progress of the submission for each UoA 
	PVCR/Research Performance/RDs
	

	· Submission window opens
	
	
	

	· Additional recruitment for assessment phase panels
	
	
	

	2027 Winter
	

	
	· 4th Equality Impact Assessment of SRR/Non-SRR Staff 
	 Head of Research Performance (ND)/EDI
	

	2028 Spring
	

	
	· REF Reviews to discuss the progress of the submission for each UoA 
	 PVCR/Research Performance/RDs
	

	
	· Final Equality Impact Assessment of SRR/Non-SRR Staff 
	Head of Research Performance (ND)/EDI
	

	2028 Autumn
	

	· Submission deadline
	
	
	

	· Assessment phase begins
	
	
	

	2029 Winter
	

	· Publication of results (planned for December 2029)
	
	
	

	
	2030
	
	

	· Publication of submitted data 
	
	
	

	· Publication of REF 2029 reports, including REF 2029 Steering Group and Panel meetings minutes and papers covering October 2026 to December 2029 (planned for March 2030)  
	
	
	


Last updated 11/06/26                                                                                                                                          2

