DRAFT REF 2029 Operational Timetable

(This timetable represents the current project plan; it will be updated as the exercise progresses).

| NATIONAL TIMELINE | ULSTER’S TIMELINE | R&I Lead/Team |  |
| --- | --- | --- | --- |
| 2025 Spring |  |  |  |
|  | - Develop first draft of the Code of practice - REF2029 CoP Working Group initial meeting - University wide consultation on the processes within Code of Practice | Head of Research Performance (ND) |  |
| - PCE Pilot project: - submission deadline (19 March 25) - pilot panels assessing submissions | - Preparation of Institutional PCE Statement (FC) - Preparation of UoA Level PCE Statements (RDs) - Completion of Feedback forms (RP Staff and RDs) (30 May 2025) | Research Performance team with Relevant RDs. |  |
| - Application closes for joining the REF panels (28 April) | - ADRIs/RDs to encourage applications | ADRIs/RDs |  |
| 2025 Summer |  |  |  |
|  | - REF Reviews to discuss the progress of the submission for each UoA, chaired by PVCR (May/June) | Research Performance/RDs |  |
|  | - 1st Equality Impact Assessment of SRR/Non-SRR Staff | Head of Research Performance & EDI Team |  |
| - Publication of Guidance on Contribution to Knowledge and Understanding Policy and Associated Codes of Practice | - Code of Practice - internal consultation with RDs | Research Performance & RDs |  |
| - Publication of Guidance on Engagement and Impact Policy |  |  |  |
| - Full panel membership announced |  |  |  |
| - PCE pilot project: sub-profile results provided to HEIs |  |  |  |
|  | - PCE Workshop | Research Performance/RDs |  |
|  | - Launch of internal REF website | Research Performance (BW) with MarComms Team |  |
| 2025 Autumn |  |  |  |
| - Onboarding of sub-panels |  |  |  |
| - HESA Staff Data 2024-25 to be used as part of pilot to calculate Volume Measure | - HESA Data on Staff for period 1st August 2024 – 31st July 2025 to be used to calculate UU’s Volume Measure as part of pilot | - Research Performance (BW and SH) will work with RDs to confirm SRR Status and ensure PeopleXD is up-to-date for the HESA Return - Research Performance to work with P&C for the HESA Staff return |  |
|  | - Code of Practice – University wide consultation | - Research Performance |  |
| - PCE Pilot Report and Indicators Report published - PCE community engagement and feedback - PCE criteria and definitions published |  |  |  |
| 2025 Winter |  |  |  |
| - Expert panels meet to begin development of guidance and criteria |  |  |  |
|  | - REF Reviews to discuss the progress of the submission for each UoA, chaired by PVCR (Jan 26) | Research Performance/RDs |  |
|  | - 2nd Equality Impact Assessment of SRR/Non-SRR Staff | Head of Research Performance/EDI |  |
| 2026 Spring |  |  |  |
| - Guidance on Submissions published for consultation |  |  |  |
| 2026 Summer |  |  |  |
|  | - REF Reviews to discuss the progress of the submission for each UoA, chaired by PVCR | Research Performance/RDs |  |
| 2026 Autumn |  |  |  |
| - Final full guidance is set |  |  |  |
| 2026 Winter |  |  |  |
| - Special requests open |  |  |  |
|  | - REF Reviews to discuss the progress of the submission for each UoA, chaired by PVCR | Research Performance/RDs |  |
|  | - 3rd Equality Impact Assessment of SRR/Non-SRR Staff | Head of Research Performance/EDI |  |
| 2027 Spring |  |  |  |
| - Survey of submission intentions opens |  |  |  |
| 2027 Summer |  |  |  |
|  | - REF Reviews to discuss the progress of the submission for each UoA, chaired by PVCR (May/June) | Research Performance/RDs |  |
| - Survey of submission intentions closes |  |  |  |
| - Special requests closes |  |  |  |
| 2027 Autumn |  |  |  |
| - HESA Staff Data 2025-26 and 2026-2027 to be used to calculate the final Volume Measure | - HESA Data on Staff for the two year period 1st August 2025 – 31st July 2027 to be used to calculate UU’s final Volume Measure | Research Performance (BW and SD) will work with RDs to confirm SRR Status and ensure CoreHR is up-to-date for the HESA Return |  |
| - Submission window opens |  |  |  |
| - Additional recruitment for assessment phase panels |  |  |  |
| 2027 Winter |  |  |  |
|  | - REF Reviews to discuss the progress of the submission for each UoA, chaired by PVCR (May/June) | Research Performance |  |
|  | - 4th Equality Impact Assessment of SRR/Non-SRR Staff | Head of Research Performance/EDI |  |
| 2028 Spring |  |  |  |
|  | - REF Reviews to discuss the progress of the submission for each UoA, chaired by PVCR (May/June) | Research Performance/RDs |  |
|  | - Final Equality Impact Assessment of SRR/Non-SRR Staff | Head of Research Performance/EDI |  |
| 2028 Autumn |  |  |  |
| - Submission deadline |  |  |  |
| - Assessment phase begins |  |  |  |
| 2029 Winter |  |  |  |
| - Publication of results (December) |  |  |  |